## Rollout Checklist
Google Review QR Rollout Checklist
Checklist operasional untuk 52 toko. IT/Widhy menyiapkan instruksi dan tracker, Jeppy/Marketing menyediakan QR resmi, Creative membuat artwork, Malik/VM memastikan placement, dan Erlin/Retail Operation mengoordinasikan pemasangan toko.
Total stores | 52 | All active rollout stores |  | Role | Primary responsibility
Complete | 0 | All required steps done |  | IT / Widhy | Instruksi, tutorial, tracker, standar validasi, dan support teknis.
In progress | 0 | At least one step done |  | Jeppy / Marketing | Provide official QR dan review link dari Google Business Profile.
Blocked | 0 | Needs owner follow-up |  | Creative | Masukkan QR resmi ke artwork tanpa membuat QR alternatif.
Not started | 52 | No step completed yet |  | Malik / VM | Placement, ukuran, posisi display, dan visual merchandising.
Completion rate | 0% | Complete stores divided by total |  | Erlin / Retail Ops | Distribusi material, instruksi store team, pemasangan, dan final scan test.
# | Store | Region | City | GBP owner | QR by Jeppy | Initial test | Sent to Creative | Design ready | VM placement approved | Installed by Ops | Final test | Status | Current owner | Next action | Priority | Due date | Notes | Last updated
1 | Batu Bolong Beach Street | Bali Area | Canggu | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
2 | Parc Valle Pererenan | Bali Area | Canggu | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
3 | Popular Deli Canggu | Bali Area | Canggu | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
4 | Subak Sari Canggu | Bali Area | Canggu | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
5 | Level 21 Mall | Bali Area | Denpasar | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
6 | Living World Denpasar | Bali Area | Denpasar | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
7 | Ujung Raya Street | Bali Area | Jasri | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
8 | Sidewalk Jimbaran | Bali Area | Jimbaran | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
9 | Beachwalk Shopping Center | Bali Area | Kuta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
10 | Discovery Shopping Mall | Bali Area | Kuta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
11 | Legian Street | Bali Area | Kuta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
12 | Mal Bali Galeria Extension | Bali Area | Kuta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
13 | Papaya Fresh Gallery | Bali Area | Kuta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
14 | Bali Collection | Bali Area | Nusa Dua | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
15 | Danau Tamblingan Street | Bali Area | Sanur | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
16 | ICON BALI | Bali Area | Sanur | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
17 | Seminyak Village | Bali Area | Seminyak | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
18 | Monkey Forest Road | Bali Area | Ubud | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
19 | Monkey Forest Road II | Bali Area | Ubud | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
20 | Central Market PIK | Jakarta & Sekitarnya (Jabodetabek) | Jakarta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
21 | Central Park Mall | Jakarta & Sekitarnya (Jabodetabek) | Jakarta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
22 | Gandaria City Mall | Jakarta & Sekitarnya (Jabodetabek) | Jakarta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
23 | Grand Indonesia East Mall | Jakarta & Sekitarnya (Jabodetabek) | Jakarta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
24 | K Mall at Menara Jakarta | Jakarta & Sekitarnya (Jabodetabek) | Jakarta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
25 | Kota Kasablanka | Jakarta & Sekitarnya (Jabodetabek) | Jakarta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
26 | Lippo Mall Nusantara | Jakarta & Sekitarnya (Jabodetabek) | Jakarta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
27 | Lotte Mall Jakarta | Jakarta & Sekitarnya (Jabodetabek) | Jakarta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
28 | Mall Kelapa Gading 2 | Jakarta & Sekitarnya (Jabodetabek) | Jakarta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
29 | Mall Of Indonesia | Jakarta & Sekitarnya (Jabodetabek) | Jakarta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
30 | Pondok Indah Mall 1 | Jakarta & Sekitarnya (Jabodetabek) | Jakarta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
31 | La Vela | Jakarta & Sekitarnya (Jabodetabek) | Tangerang | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
32 | Living World Alam Sutera | Jakarta & Sekitarnya (Jabodetabek) | Tangerang | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
33 | Summarecon Mall Serpong | Jakarta & Sekitarnya (Jabodetabek) | Tangerang | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
34 | Pakuwon Mall Bekasi | Jakarta & Sekitarnya (Jabodetabek) | Bekasi | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
35 | AEON MALL Deltamas | Jakarta & Sekitarnya (Jabodetabek) | Cikarang | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
36 | MARGOCITY | Jakarta & Sekitarnya (Jabodetabek) | Depok | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
37 | Cibinong City Mall | Jakarta & Sekitarnya (Jabodetabek) | Cibinong | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
38 | Paris Van Java Lifestyle Resort | Jawa & Area Lainnya | Bandung | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
39 | Summarecon Mall Bandung | Jawa & Area Lainnya | Bandung | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
40 | Pakuwon City Mall | Jawa & Area Lainnya | Surabaya | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
41 | Pakuwon Mall Surabaya | Jawa & Area Lainnya | Surabaya | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
42 | Tunjungan Plaza 3 | Jawa & Area Lainnya | Surabaya | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
43 | 23 Semarang Shopping Center | Jawa & Area Lainnya | Semarang | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
44 | Pakuwon Mall Jogja | Jawa & Area Lainnya | Yogyakarta | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
45 | Delipark Mall | Sumatera, Sulawesi, & Nusa Tenggara | Medan | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
46 | Sun Plaza | Sumatera, Sulawesi, & Nusa Tenggara | Medan | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
47 | One Batam Mall | Sumatera, Sulawesi, & Nusa Tenggara | Batam | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
48 | Palembang Indah Mall | Sumatera, Sulawesi, & Nusa Tenggara | Palembang | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
49 | Mal Ratu Indah | Sumatera, Sulawesi, & Nusa Tenggara | Makassar | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
50 | Trans Studio Mall Makassar | Sumatera, Sulawesi, & Nusa Tenggara | Makassar | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
51 | Lombok Epicentrum Mall | Sumatera, Sulawesi, & Nusa Tenggara | Lombok | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal
52 | Mawatu at Labuan Bajo | Sumatera, Sulawesi, & Nusa Tenggara | Labuan Bajo | Jeppy / Marketing | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not Started | Jeppy / Marketing | Provide official QR for this store | Normal